## Tracker
Category | Task | Status | Start Date | End Date | Notes
Terraform - VPC | Create VPC module | Completed | 2026-04-13 | 2026-04-13
Terraform - VPC | Create subnets (public/private) | Completed | 2026-04-13 | 2026-04-13
Terraform - VPC | Add IGW and NAT Gateway | Completed | 2026-04-13 | 2026-04-13
Terraform - EKS | Create EKS cluster | Completed | 2026-04-13 | 2026-04-13
Terraform - EKS | Add node group | Completed | 2026-04-13 | 2026-04-13
Terraform - RDS | Create RDS instance (private) | Completed | 2026-04-13 | 2026-04-13
Terraform - IAM | Create IAM roles for EKS | Completed | 2026-04-13 | 2026-04-13
Terraform - IAM | Setup GitHub OIDC | Completed | 2026-04-13 | 2026-04-13
Environment Setup | Connect modules in dev env | In Progress | 2026-04-14
Environment Setup | Terraform init & apply
Kubernetes | Configure kubectl access
Kubernetes | Deploy frontend via Helm
Kubernetes | Deploy backend via Helm
CI/CD | Build Docker images
CI/CD | Push images to ECR
CI/CD | Deploy via GitHub Actions
Security | Add Trivy scan
Monitoring | Install Prometheus & Grafana
Documentation | Write README | In Progress | 2026-04-13
Documentation | architecture

## Metrics
Total Tasks | 17
Completed | 8
In Progress | 2
Not Started | 0
Progress % | 0.8